## Instructions
This file is setup for implementation task tracking by assigned groups for the Town Plan.
This file is setup to update a master file for all of the Implementation tasks assigned to various groups in support of the Town Plan
Certain cells are locked to maintain formatting consistency necessary to link to the master file.
Input for each assigned group is as follows:
Column A - this field is used to indicate completion of the task. Milestones are 25%, 50%, 75%, and 100%.
Columns B, C, D, & E - are from the Implementation Tasks from the Town Plan and greyed out indicating no need to edit.
Column F - is for notes to be used for summarizing status in the master file for all groups to see.
Column G - is for use by the assigned group if they want to prioritize their tasks.
Column H (non-editable) is the rank for the assigned group from the Town Plan of responsibility if multiple groups are involved with the task
(1 = primary, 2 = secondary, 3 = tertiary).
Columns H, I, & J - are from the Implementation Tasks from the Town Plan and greyed out indicating no need to edit.
Columns L, M, & N are hidden columns with some sort values.

## Worksheet
Implementation Plan Actions - Conservation Commission
% compl number | % Complete | Section Description | Sub-Section Description | Action | Progress | Priority | Level Resp | Responsible | Schedule | SEC_NUM | SUB_NUM | ACT_NUM
0 | 0 | The Community | Scenic, Historic, & Cultural Resources | 2. Identify significant public scenic resources. |  |  | 2 | Conservation Commission | 5 years | 20 | 20 | 2
0 | 0 | The Community | Recreation & Healthy Living | 2. Maintain existing public facilities and outdoor spaces that encourage social and leisure time activities among town residents. | Bristol parks websites |  | 3 | Conservation Commission | ongoing | 20 | 60 | 2
0 | 0 | The Community | Natural Resources & Forest Blocks | 1. Strive to maintain and improve public access to the New Haven River, Baldwin Creek and Bristol Pond. | ongoing maintainence and opportunistic |  | 2 | Conservation Commission | ongoing | 20 | 110 | 1
0 | 0 | The Community | Natural Resources & Forest Blocks | 2. Develop a management plan to minimize introduction of invasive species into Bristol’s natural communities on town properties. | included in park management plans and possibly can involve Middlebury students | high | 1 | Conservation Commission | 5 years | 20 | 110 | 2
0 | 0 | The Community | Natural Resources & Forest Blocks | 3. Develop education and outreach materials for landowners about Rare/Threatened/Endangered species and how to develop a management plan for these sites. | included in park management plans and possibly can involve Middlebury students | high | 1 | Conservation Commission | ongoing | 20 | 110 | 3
0 | 0 | The Community | Natural Resources & Forest Blocks | 4. Work with adjacent towns, local groups, state agencies and willing land owners to develop low environmental impact biking and hiking trails that promote access to natural resource areas. | colloborate with the BTN and rec as opportunities arise |  | 2 | Conservation Commission | ongoing | 20 | 110 | 4
0 | 0 | The Community | Natural Resources & Forest Blocks | 5. Evaluate opportunities to conserve lands with high natural resource value, especially those adjacent to town-owned or already conserved properties, through purchase in fee simple or funding of conservation easements. | this is fairly opportunistic |  | 2 | Conservation Commission | ongoing | 20 | 110 | 5
35 | 35 | The Community | Natural Resources & Forest Blocks | 6. Develop individual management plans for town parks | there are rough drafts that are a high priority for us to discuss, possibly with Middebury college students | high | 1 | Conservation Commission | 3 years | 20 | 110 | 6
0 | 0 | The Community | Flood Resilience | 8. Consider river corridor conservation and protection measures to decrease flood erosion losses and increase flood resiliency and discourage additional infrastructure in the river corridor area. | continue the conversation with citizens and the town to balance the costs/benefits of river corridor bylaws |  | 2 | Conservation Commission | 5 years | 20 | 120 | 8

## Reference Implementation Plan
Section | Sub-section | Action | Primary Responsibility | Secondary Responsibility | Tertiary Responsibility | Schedule
The People | POPULATION & HOUSING | 1. Conduct a Housing Study to identify the housing needs of the Bristol community and review the impacts of short-term rentals on current housing stock. | Planning Commission |  |  | 3 years
The People | POPULATION & HOUSING | 2. Update Zoning/Unified Development Regulations to allow a variety of housing types to accommodate all segments of the community. | Planning Commission |  |  | 5 years
The Community | SCENIC, HISTORIC, & CULTURAL RESOURCES | 1. Maintain inventory of significant historic structures, sites and districts. | Planning Commission |  |  | Ongoing
The Community | SCENIC, HISTORIC, & CULTURAL RESOURCES | 2. Identify significant public scenic resources. | Conservation Commission | Planning Commission |  | 5 years
The Community | MUNICIPAL FACILITIES & LANDS | 1. Review and inspect all town facilities and buildings periodically, ensuring that insurance and maintenance protects the town’s investments. | Selectboard |  |  | ongoing
The Community | MUNICIPAL FACILITIES & LANDS | 2. Develop long-term plan for major renovation (if needed) of all the town-owned buildings including the schedule and possible funding sources. | Selectboard |  |  | 5 years
The Community | ECONOMIC DEVELOPMENT | 1. Assess the needs of small to mid-size commercial and light-industrial businesses that are compatible with the character of the town. | Planning Commission |  |  | 1-5 years
The Community | ECONOMIC DEVELOPMENT | 2. Maintain and promote the Downtown Designation to enhance the economic vitality of the downtown area. | Selectboard |  |  | Ongoing
The Community | ECONOMIC DEVELOPMENT | 3. Use the Bristol Revolving Loan Fund (RLF) to attract new businesses and support existing businesses. | Selectboard |  |  | Ongoing
The Community | EDUCATION & CHILDCARE | 1. Support the Mt Abe Unified School District (MAUSD) in determining the 5-town future school structure. | Selectboard |  |  | ongoing
The Community | EDUCATION & CHILDCARE | 2. Nominate representatives to actively participate on Mt Abe Unified School District (MAUSD) School Board | Selectboard |  |  | ongoing
The Community | EDUCATION & CHILDCARE | 3. Identify steps that can be taken to meet the child care needs of Bristol. | Planning Commission |  |  | 1-3 years
The Community | RECREATION & HEALTHY LIVING | 1. Continue work planning for a new or renovated recreation center to replace the aging Hub. | Recreation Department | Selectboard |  | 1 year
The Community | RECREATION & HEALTHY LIVING | 2. Maintain existing public facilities and outdoor spaces that encourage social and leisure time activities among town residents. | Selectboard | Recreation Dept. | Conservation Commission | ongoing
The Community | UTILITIES | 1. Explore alternative sewage treatment options to accommodate new development. | Selectboard |  |  | 3 years
The Community | UTILITIES | 2. Maintain current Operation and Maintenance Manuals for the town’s service departments (i.e. Public Works, Water and Sewer Departments) that address technical standards and requirements and ensure continuity in their operations when there are staffing changes. | Selectboard |  |  | on-going
The Community | TRANSPORTATION | 1. Continue efforts to make the town and village pedestrian and bicycle-friendly and accessible to people with disabilities. | Selectboard | Planning Commission |  | ongoing
The Community | TRANSPORTATION | 2. Nominate a Bristol representative to sit on the Walk-Bike Council of Addison County to foster safe and accessible opportunities for walking and cycling as an alternative to single occupancy vehicles. | Selectboard | Energy Committee |  | 1 year
The Community | ENERGY | 1. Work toward implementing the goals and policies as described in the Enhanced Energy Plan to help meet the State’s 2016 Comprehensive Energy Plan targets. | Selectboard | Planning Commission | Energy Committee | ongoing
The Community | ENERGY | 2. Maintain current energy resources and information on the town website. | Energy Committee |  |  | ongoing
The Community | PUBLIC HEALTH & SAFETY | 1. Update and implement Local Emergency Management Plan and Local Hazard Mitigation Plan. | Selectboard | Town Manager | EMD | Annually
The Community | PUBLIC HEALTH & SAFETY | 2. Re-examine the purpose of our police force and how best to achieve that purpose. | Selectboard |  |  | ongoing
The Community | PUBLIC HEALTH & SAFETY | 3. Conduct feasibility study for protecting the village spring from contamination due to flooding. | Town Administrator | Water Department |  | 3 years
The Community | NATURAL RESOURCES & FOREST BLOCKS | 1. Strive to maintain and improve public access to the New Haven River, Baldwin Creek and Bristol Pond. | Planning Commission | Conservation Commission |  | ongoing
The Community | NATURAL RESOURCES & FOREST BLOCKS | 2. Develop a management plan to minimize introduction of invasive species into Bristol’s natural communities on town properties. | Conservation Commission |  |  | 5 years
The Community | NATURAL RESOURCES & FOREST BLOCKS | 3. Develop education and outreach materials for landowners about Rare/Threatened/Endangered species and how to develop a management plan for these sites. | Conservation Commission |  |  | ongoing
The Community | NATURAL RESOURCES & FOREST BLOCKS | 4. Work with adjacent towns, local groups, state agencies and willing land owners to develop low environmental impact biking and hiking trails that promote access to natural resource areas. | Planning Commission | Conservation Commission |  | ongoing
The Community | NATURAL RESOURCES & FOREST BLOCKS | 5. Evaluate opportunities to conserve lands with high natural resource value, especially those adjacent to town-owned or already conserved properties, through purchase in fee simple or funding of conservation easements. | Planning Commission | Conservation Commission |  | ongoing
The Community | NATURAL RESOURCES & FOREST BLOCKS | 6. Develop individual management plans for town parks | Conservation Commission | Bristol Recreation Department |  | 3 years
The Community | FLOOD RESILIENCE | 1. Improve storm water capacity on Mountain Terrace and East Street. | Selectboard | Town Administrator |  | 5 years
The Community | FLOOD RESILIENCE | 2. Expand storm water capacity in the Mountain Street/ Crescent Street area to meet a minimum 10-year flooding event. | Selectboard | Town Administrator |  | 5 years
The Community | FLOOD RESILIENCE | 3. Replace and upgrade storm water system along Spring Street and North Street to prevent flooding damage to the elementary school during heavy rain events. | Selectboard | Town Administrator |  | 5 years
The Community | FLOOD RESILIENCE | 4. Participate in National Flood Insurance Program training when offered by State/FEMA. | Zoning Administrator |  |  | ongoing
The Community | FLOOD RESILIENCE | 5. Explore options to stabilize intersection of Basin Street where it meets East St./Rte. 17 | Selectboard |  |  | ongoing
The Community | FLOOD RESILIENCE | 6. Stabilize bank/ditch along Upper Notch Road. | Selectboard
The Community | FLOOD RESILIENCE | 7. Maintain adequate stream bank buffers and existing setbacks that recognize the dynamic nature of the New Haven River | Planning Commission |  |  | 3 years
The Community | FLOOD RESILIENCE | 8. Consider river corridor conservation and protection measures to decrease flood erosion losses and increase flood resiliency and discourage additional infrastructure in the river corridor area. | Planning Commission | Conservation Commission | Selectboard | 5 years
Land Use and Planning |  | 1. Review all existing zones and conform zoning changes to the adopted Town Plan. | Planning Commission |  |  | 3 years
Land Use and Planning |  | 2. Promote incentives and programs to encourage business and light industry investment and growth | Selectboard | Town Administrator |  | Ongoing